## Sheet1
PROCUREMENT PLAN FOR ENERGY DEVELOPMENT CORPORATION LIMITED 2025-2026
S/N | Description | Source of Funds | Tendering method ( ICB, NCB,IRT, NRT,RFQ, SS, Community Approach, framework contract, QCBS ,etc.) | Planned tender document preparation date | Planned Publication date | Planned Bid opening date | Planned Provisional Notification date | Planned Contract signing date | Recruitment of the supervising firm (Yes/Non) | Planned Contract Management start date | Contract End
I. WORKS
ORDINARY BUDGET
1 | Office Partitioning, Supply and installation of Air conditioners | GoR | NCB | 2025-09-18 | 2025-11-17 | 2026-01-02 | 2026-05-07 | 2026-05-27 | YES | 2026-05-27 | 2026-11-23
2 | Purchase the existing Arc Power’s power distribution assets for electrification of Murama village | GoR | SS | 2025-08-18 | 2025-09-08 | 2025-10-23 | 2025-11-07 | 2025-11-21 | YES | 2025-11-21 | 2026-11-16
3 | Design, supply and installation (EPC) for the replacement of Old 15MVA 6.6/110kV transformer by a new one 15MVA and in-door MV Gas insulated switch gear at Mukungwa | GoR | ICB | 2025-11-21 | 2025-12-11 | 2026-01-26 | 2026-05-26 | 2026-06-25 | YES | 2026-06-25 | 2028-06-14
4 | Design, supply and installation (EPC) for Low Voltage AC/DC distribution installation (auxiliary power supply) for Gikondo & Jabana Substations | GoR | NCB | 2025-11-20 | 2025-12-10 | 2026-01-26 | 2026-05-26 | 2026-06-25 | YES | 2026-06-25 | 2028-06-14
SUB TOTAL
RWANDA UNIVERSAL ELECTRICITY ACCESS PROGRAM "RUEAP" (USD converted in RWF, USD= 1436.7123
5 | Design, Supply, and Installation of low voltage and medium voltage lines and service connections in Ngoma & Kirehe district | WB/ASCENT | ICB | 2025-07-18 | 2025-09-16 | 2025-10-31 | 2026-02-28 | 2026-03-15 | YES | 2026-03-15 | 2028-03-04
6 | Design, Supply, and Installation of low voltage and medium voltage lines and service connections in Nyagatare district | WB/ASCENT | ICB | 2025-07-18 | 2025-09-16 | 2025-10-31 | 2026-02-28 | 2026-03-15 | YES | 2026-03-15 | 2028-03-04
7 | Design, Supply, and Installation of low voltage and medium voltage lines and service connections in Karongi district | WB/ASCENT | ICB | 2025-06-03 | 2025-06-10 | 2025-07-18 | 2025-11-15 | 2026-01-14 | YES | 2026-01-14 | 2028-01-04
8 | Design, Supply, and Installation of low voltage and medium voltage lines and service connections in Nyabihu & Rubavu district | WB/ASCENT | ICB | 2025-08-07 | 2025-08-14 | 2025-09-29 | 2026-02-13 | 2026-04-11 | YES | 2026-04-11 | 2028-03-31
9 | Design, Supply, and Installation of low voltage and medium voltage lines and service connections in Rusizi district | WB/ASCENT | ICB | 2025-07-01 | 2025-07-01 | 2025-07-31 | 2025-11-28 | 2026-01-27 | YES | 2026-01-27 | 2028-01-17
10 | Design, Supply, and Installation of low voltage and medium voltage lines and service connections in Rutsiro district | WB/ASCENT | ICB | 2025-07-01 | 2025-07-01 | 2025-07-31 | 2025-11-28 | 2026-01-27 | YES | 2026-01-27 | 2028-01-17
11 | Design, Supply, and Installation of low voltage and medium voltage lines and service connections in Burera& Gakenke district | WB/ASCENT | ICB | 2025-08-12 | 2025-09-12 | 2025-11-11 | 2026-04-10 | 2026-05-10 | YES | 2026-05-10 | 2028-04-29
12 | Design, Supply, and Installation of low voltage and medium voltage lines and service connections in Gicumbi& Rurindo district | WB/ASCENT | ICB | 2025-09-05 | 2025-09-12 | 2025-11-11 | 2026-04-10 | 2026-05-10 | YES | 2026-05-10 | 2028-04-29
13 | Design, Supply, and Installation of low voltage and medium voltage lines and service connections in Gasabo district | WB/ASCENT | ICB | 2025-10-01 | 2025-10-06 | 2025-12-05 | 2026-04-03 | 2026-06-03 | YES | 2026-06-03 | 2028-05-23
14 | Design, Supply, and Installation of low voltage and medium voltage lines and service connections in Kicukiro district | WB/ASCENT | ICB | 2025-10-01 | 2025-10-06 | 2025-12-05 | 2026-04-03 | 2026-06-03 | YES | 2026-06-03 | 2028-05-23
15 | Construction of 220kV double circuit transmission line connecting Bwishyura Substation to Kigoma substation (56km) | WB/ASCENT | ICB | 2024-11-28 | 2025-01-27 | 2025-03-13 | 2025-07-11 | 2025-07-26 | YES | 2025-07-26 | 2027-01-17
16 | Construction of modern kitchens in 35 schools | WB/EAQIP | NCB | 2025-05-01 | 2025-05-13 | 2025-06-18 | 2025-10-16 | 2025-10-31 | YES | 2025-10-31 | 2027-04-24
SUB TOTAL
16 | TOTAL WORKS
II. GOODS AND OTHER SERVICES
ORDINARY BUDGET
1 | Provision of Sports and recreational facilities and services under framework contract | GoR | NCB | 2025-07-21 | 2025-08-07 | 2025-09-22 | 2025-10-13 | 2025-10-27 | N/A | 2025-10-27 | 2026-10-27
2 | Provision of casual workers for Energy Development Corporation Ltd | GoR | Force account | 2025-06-28 | 2025-07-15 | 2025-08-29 | 2025-09-19 | 2025-10-03 | N/A | 2025-10-03 | 2026-10-03
3 | Provision of Hotel Services & outside catering services under framework contract | GoR | NCB | 2025-09-19 | 2025-10-06 | 2025-11-20 | 2025-12-11 | 2025-12-30 | N/A | 2025-12-30 | 2026-12-30
4 | Repair, maintenance, and supply of materials, spare parts, or accessories for air conditioners, plumbing systems, and electricity installations under frame work contract | GoR | NCB | 2025-09-15 | 2025-10-02 | 2025-11-17 | 2025-12-08 | 2025-12-22 | N/A | 2025-12-22 | 2026-12-17
5 | Provision of restaurant service to EDCL Staff under frame work contract | GoR | NCB | 2025-09-15 | 2025-10-02 | 2025-11-17 | 2025-12-08 | 2025-12-22 | N/A | 2025-12-22 | 2026-12-22
6 | Supply of electrical wooden poles under framework contract | GoR | SS/UFCL | 2025-08-14 | 2025-08-29 | 2025-10-13 | 2025-11-03 | 2025-11-17 | N/A | 2025-11-17 | 2026-11-17
7 | Supply, Installation and Training for AutoCAD software for planning department | GoR | NCB | 2025-10-15 | 2025-11-03 | 2025-12-18 | 2026-01-08 | 2026-01-22 | N/A | 2026-01-22 | 2027-01-17
SUB TOTAL
RWANDA UNIVERSAL ELECTRICITY ACCESS PROGRAM "RUEAP" (USD converted in RWf, USD= 1436.7123
8 | Supply of Forklifts, spider crane and logger machines | WB/ASCENT | NCB | 2025-07-18 | 2025-07-24 | 2025-08-25 | 2025-10-14 | 2025-11-04 | N/A | 2025-11-04 | 2026-04-03
9 | Supply of office furnitures | WB/ASCENT | NCB | 2025-07-21 | 2025-07-24 | 2025-08-25 | 2025-10-23 | 2025-11-13 | N/A | 2025-11-13 | 2026-04-13
10 | Supply of IT equipments | WB/ASCENT | NCB | 2025-07-23 | 2025-07-28 | 2025-08-28 | 2025-10-16 | 2025-11-03 | N/A | 2025-11-03 | 2026-03-03
11 | Supply and installation of clean cooking systems in 33 schools | WB/EAQIP | ICB | 2025-05-01 | 2025-05-13 | 2025-06-30 | 2025-10-28 | 2025-11-12 | YES | 2025-11-12 | 2027-05-06
SUB TOTAL
BADEA II
12 | Supply of electrical materials for BADEA Project | BADEA II | ICB | 2025-02-10 | 2025-03-12 | 2025-04-25 | 2025-06-09 | 2025-11-06 | N/A | 2025-11-06 | 2026-11-05
SUB TOTAL
12 | TOTAL GOODS
III. CONSULTANCY SERVICES
ORDINARY BUDGET
1 | Feasibility study Rusizi III and Associated lines (Bwishyura-Kamanyola) | GoR | QCBS | 2025-06-10 | 2025-07-25 | 2025-09-08 | 2025-10-23 | 2025-11-21 | N/A | 2025-11-21 | 2027-11-19
2 | Hiring a Consultant for the Development and implementation of the Nyabarongo II Carbon Project | GoR | QCBS | 2025-07-24 | 2025-07-29 | 2025-09-12 | 2025-11-11 | 2025-12-30 | N/A | 2025-12-30 | 2029-09-30
3 | Hiring an Individual Consultant to Develop a Business Plan and Provide Capacity Building Assistance for the EPC Department | GoR | QCBS | 2025-08-25 | 2025-10-24 | 2025-12-08 | 2026-02-06 | 2026-03-27 | N/A | 2026-03-27 | 2029-09-30
SUB TOTAL
RWANDA UNIVERSAL ELECTRICITY ACCESS PROGRAM "RUEAP" (USD converted in RWf, USD= 1436.7123
4 | Hiring consultant firm for supervision for Access projects ( Batch1) | WB/ASCENT | QCBS | 2025-01-01 | 2025-01-10 | 2025-04-10 | 2025-01-30 | 2025-10-07 | N/A | 2025-10-07 | 2029-09-16
5 | Hiring consultant firm for supervision for Access projects ( Batch2) | WB/ASCENT | QCBS | 2025-07-18 | 2025-10-09 | 2025-11-27 | 2026-03-26 | 2026-04-06 | N/A | 2026-04-06 | 2030-03-16
6 | Hiring consultant firm for supervision for transmission and distribution projects | WB/ASCENT | QCBS | 2025-04-25 | 2025-04-30 | 2025-05-30 | 2025-06-29 | 2025-07-28 | N/A | 2025-07-28 | 2029-07-07
7 | Feasibility study for utility scale Solar PV integrating storage countrywide | WB/ASCENT | QCBS/ICB | 2025-08-20 | 2025-08-25 | 2025-12-03 | 2026-03-03 | 2026-04-02 | N/A | 2026-04-02 | 2026-09-29
8 | Hiring consultant firm for Review and Update of Rwanda’s Biomass Strategy | WB /EAQIP | QCBS/ICB | 2025-08-05 | 2025-08-20 | 2025-09-22 | 2025-12-19 | 2026-01-20 | N/A | 2026-01-20 | 2026-09-17
9 | Feasibility study of REG Control Center and Communication Building | AfDB | QCBS/ICB | 2025-07-18 | 2025-07-23 | 2025-08-22 | 2025-09-12 | 2025-10-10 | N/A | 2025-10-10 | 2026-06-07
10 | Consulting Services for the Supervision of Clean Institutional Cooking Systems in Schools and Feasibility Analysis for Extension to More Schools | WB/ASCENT | QCBS/NCB | 2025-08-18 | 2025-08-22 | 2025-09-22 | 2025-10-13 | 2025-11-10 | N/A | 2025-11-10 | 2026-07-08
11 | Hiring consultant firm for Tender Document Preparation and Project Supervision of design, Supply and Installation of Power System Stabilizers and Governing Systems on Main Generators at Nyabarongo 1 HPP. | WB/ASCENT | QCBS/ICB | 2025-08-20 | 2025-08-25 | 2025-10-30 | 2025-12-29 | 2026-04-02 | N/A | 2026-04-02 | 2026-09-30
SUB TOTAL
11 | TOTAL SERVICES
39 | TOTAL GENERAL
Done on 30th June 2025
| Prepared by | [7 empty] | Approved by
| NSHOGOZA SIKUBWABO | [7 empty] | Felix GAKUBA
| Manager contract management | [7 empty] | Managing Director
Formulas:
Planned Publication date = [Planned tender document preparation date]+60
Planned Publication date = [Planned tender document preparation date]
Planned Bid opening date = [Planned Publication date]+46
Planned Provisional Notification date = [Planned Bid opening date]+125
Planned Contract signing date = [Planned Provisional Notification date]+20
Planned Contract Management start date = [Planned Contract signing date]
Contract End = [Planned Contract Management start date]+6*30
Contract End = [Planned Contract Management start date]+720